## Final
|  |  | Group 2 | Product Backlog |  |  |  |  | # | ID | Days | Left Days | Start Date | End Date
|  |  | Rental Car Project | "Europcar" |  |  |  |  | Sprint 1 | 1,2,5 | 28 | -43 | 2019-03-28 | 2019-04-25
|  |  | Deadline Estimate / Today | 2019-06-07 | 2019-06-07 | Left days: | 0 |  | Sprint 2 | 3,4,6,8,9,11 | 21 | -22 | 2019-04-25 | 2019-05-16
|  |  | How many percent are done | 100 |  | yeeees, we dit it :) |  |  | Sprint 3 | 12.13 | 6 | -16 | 2019-05-16 | 2019-05-22 | Analyze and designe
|  |  | ? | ? |  |  |  |  | Sprint 4 | 8,10,14 | 5 | -11 | 2019-05-22 | 2019-05-27 | Documentation
|  |  | ? | ? | ? |  |  |  | Sprint 5 | 7 | 3 | -8 | 2019-05-27 | 2019-05-30 | BurnDown Chart
|  |  | Number of hours Estimate/Actual | 185 | 183.45 |  |  |  | Sprint 6 | Doc | 4 | -4 | 2019-05-30 | 2019-06-03 | Goup contract
[9 empty] | Sprint 7 | Doc | 4 | 0 | 2019-06-03 | 2019-06-07
Product Backlog | [8 empty] | Total |  | 71
ID | Priority | Estimate | Item | Day 1 | Day 2 | Day 3
1 | Critical | 20 | As a user, I want to be able to rent a car in order to drive. | 15 | 8 | 9 | +
2 | High | 15 | As a user, I want to be able to select a certain type of vehicle in order to find a vehicle that suits my needs. | 10 | 8 | 6.5 | +
3 | Medium | 10 | As a user, I want to be able to select additional services in order to ease my journey. | 3.2 | 0.75 | 0.75 | + | Velocity Chart
4 | Low |  | As a user, I want the system to save my credentials in order to make it easier next time renting a vehicle.
5 | High | 20 | As a user, I want to be able to select the number of days I want to rent the vehicle in order to reserve the vehicle. | 5 | 4.5 | 3.5 | +
6 | Mid low | 10 | As a user, I want to be able to see the pricing of different vehicles in order to select a vehicle inside my budget. | 2.5 | 3 | 1.5 | +
7 | Medium | 5 | As a user, I want to be able to cancel my reservation in order to not rent a vehicle. | 5 | 2 | 3
8 | Low | 15 | As a user, I want to be notified if changes occur to my reservation, in order to be able to change my reservation | 7 | 5 | 3 | +
9 | High | 25 | As a user, I want to receive a booking confirmation by email, in order to have proof of reservation. | 4.25 | 2 | 1 | +
10 | Low | 20 | As an administrator, I want to be able to select the prices of different cars, in order to control prices. | 7 | 4 | 2 | +
11 | High | 15 | As an administrator, I want to be able to access my customers credentials in order to be able to contact them. | 4.5 | 2.5 | 3 | +
12 | High | 10 | As an administrator, I want to be able to see what vehicles are currently rented out, in order to see what is available. | 8 | 6 | 5.5 | +
13 | Mid low | 10 | As an administrator, I want to be able to select extra services provided, in order to ease the journey of the customer. | 1 | 8 | 6.5 | +
14 | Medium | 10 | As a user, I want to be able to add money to my wallet | 8 | 3 | 1 | +
Total |  | 185 |  | 80.45 | 56.75 | 46.25
183.45

## Sprint 1
|  |  |  | Group 2 | Product Backlog
|  |  |  | Rental Car Project | "Europcar"
|  |  |  | Deadline Estimate / Today | 2019-06-07 | 2019-06-07 | Left days: | 0
|  |  |  | How many percent are done | 100
|  |  |  | ? | ? |  | Done
|  |  |  | ? | ? | ? | In Progres
|  |  |  | Number of hours Estimate/Actual | 55 | 69.5 | Not Started
Product Backlog
ID | Priority | Responsible | Estimate | Item | Day 1 | Day 2 | Day 3
1 | Critical |  | 20 | As a user, I want to be able to rent a car in order to drive. | 15 | 8 | 9
|  | Justinas |  | Use case diagram and description | 1 | 1 | 0
|  | Justinas |  | Sequence Diagram | 1 | 0 | 0 |  | Velocity Chart
|  | Justinas |  | Activity Diagram | 1 | 0 | 0
|  | Justinas |  | Create a domain model | 0 | 2 | 0
|  | Justinas |  | Create a logical model | 0 | 1 | 0
|  | Justinas |  | Create the user class | 0 | 0 | 1
|  | Justinas |  | Create the car class | 0 | 0 | 1
|  | Justinas |  | Create the database | 5 | 0 | 0
|  | Justinas |  | Generate some data for testing | 3 | 4 | 0
|  | Justinas |  | Program the server to give car list | 2 | 0 | 3
|  | Justinas |  | Program the client renting | 2 | 0 | 4
2 | High |  | 15 | As a user, I want to be able to select a certain type of vehicle in order to find a vehicle that suits my needs. | 10 | 8 | 6.5
|  | Nicoleta\Dima |  | Use Case Diagram | 0.5 | 0.5 | 0.5
|  | Nicoleta |  | Use Case Descrition | 1 | 1 | 1
|  | Nicoleta |  | Activity Diagram | 0.5 | 0.5 | 0.5
|  | Dima |  | Class Diagram | 1 | 1 | 0.5
|  | Dima |  | Create GUI | 3 | 2 | 1
|  | Dima |  | Create connection between 4 windows in GUI(Login,Registration, Search Car Option as a Guest and Search Car Option) | 3 | 3 | 2
|  |  |  | Testing | 1 | 0 | 1
5 | High | Simona | 20 | As a user, I want to be able to select the number of days I want to rent the vehicle in order to reserve the vehicle. | 5 | 4.5 | 3.5
|  | Justinas |  | Use Case Diagram | 0.5 | 0.5 | 0.5
|  | Nicoleta |  | Use Case Diagram | 2 | 2 | 1
|  | Dima |  | Use Case Diagram | 1 | 1 | 1
|  | Dima |  | Use Case Diagram | 1.5 | 1 | 1
Total |  |  | 55 |  | 30 | 20.5 | 19
69.5

## Sprint 2
|  |  |  | Group 2 | Product Backlog
|  |  |  | Rental Car Project | "Europcar"
|  |  |  | Deadline Estimate / Today | 2019-06-07 | 2019-06-07 | Left days: | 0
|  |  |  | How many percent are done | 102.0833
|  |  |  | ? | ? |  | Done
|  |  |  | ? | ? | ? | In Progres
|  |  |  | Number of hours Estimate/Actual | 60 | 28.95 | Not Started
Product Backlog
ID | Priority | Responsible | Estimate | Item | Day 1 | Day 2 | Day 3
3 | Medium | Nicoleta | 10 | As a user, I want to be able to select additional services in order to easy my journey | 3.2 | 0.75 | 0.75
|  |  |  | Uase case diagram | 0.2 | 0.5 | 0
|  |  |  | Activity Diagram | 2 | 0 | 0.5 |  | Velocity Chart
|  |  |  | Create GUI | 1 | 0.25 | 0.25
11 | High | Dima | 15 | As an administrator, I want to be able to access my customers credentials in order to be able to contact them. | 4.5 | 2.5 | 3
|  |  |  | Create Booked tab for customers who booket at least one time | 2 | 2 | 2
|  |  |  | Get Data from database and create SQL statement | 1 | 0 | 0
|  |  |  | Testing | 1 | 0 | 1
|  |  |  | Documentation | 0.5 | 0.5 | 0
6 | High | Nicoleta | 10 | As a user, I want to be able to see the pricing of different vehicles in order to select a vehicle inside my budget. | 2.5 | 3 | 1.5
|  |  |  | Activity Diagram | 1 | 1 | 0.5
|  |  |  | Use Case diagram | 0.25 | 0 | 0
|  |  |  | Use case description | 0.25 | 0 | 0
|  |  |  | Class Diagram | 1 | 2 | 1
9 | High | Justinas | 25 | As a user, I want to receive a booking confirmation by email, in order to have proof of reservation. | 4.25 | 2 | 1
|  |  |  | Update the use case diagram | 1 | 1 | 0
|  |  |  | Update the sequence diagram | 1 | 0 | 1
|  |  |  | Implement a notification that an email is sent | 1 | 1 | 0
| low |  |  | Create SMTP or implement an existing one | 0.25 | 0 | 0
| low |  |  | Create the send an email method | 1 | 0 | 0
Total |  |  | 60 |  | 14.45 | 8.25 | 6.25
28.95

## Sprint 3
|  |  |  | Group 2 | Product Backlog
|  |  |  | Rental Car Project | "Europcar"
|  |  |  | Deadline Estimate / Today | 2019-06-07 | 2019-06-07 | Left days: | 0
|  |  |  | How many percent are done | 90
|  |  |  | ? | ? |  | Done
|  |  |  | ? | ? | ? | In Progres
|  |  |  | Number of hours Estimate/Actual | 20 | 26.5 | Not Started
Product Backlog
ID | Priority | Responsible | Estimate | Item | Day 1 | Day 2 | Day 3
12 | Medium | Dima/Justinas | 10 | As an administrator, I want to be able to see what vehicles are currently rented out, in order to see what is available. | 8 | 6 | 5.5
|  |  |  | Use case diagram | 1 | 1 | 1
|  |  |  | Activity diagram | 1 | 1 | 1 |  | Velocity Chart
|  |  |  | Sql statements | 2 | 1 | 0.5
|  |  |  | Available Cars Tab | 2 | 2 | 1
|  |  |  | Booked Cars Tab | 2 | 1 | 0.5
|  |  |  | Testing each case | 0 | 0 | 1.5
Documentation
13 | Mid low | Nicoleta | 10 | As an administrator, I want to be able to select extra services provided, in order to ease the journey of the customer. | 1 | 3 | 3
|  |  |  | Activity diagram | 0 | 1 | 1
|  |  |  | Use case diagram | 0 | 1 | 1
|  |  |  | GUI | 1 | 1 | 1
Total |  |  | 20 |  | 9 | 9 | 8.5
26.5

## Sprint 4
|  |  |  | Group 2 | Product Backlog
|  |  |  | Rental Car Project | "Europcar"
|  |  |  | Deadline Estimate / Today | 2019-06-07 | 2019-06-07 | Left days: | 0
|  |  |  | How many percent are done | 100
|  |  |  | ? | ? |  | Done
|  |  |  | ? | ? | ? | In Progres
|  |  |  | Number of hours Estimate/Actual | 45 | 40 | Not Started
Product Backlog
ID | Priority | Responsible | Estimate | Item | Day 1 | Day 2 | Day 3
8 | Low | Justinas | 15 | As a user, I want to be notified if changes occur to my reservation, in order to be able to change my reservation | 7 | 5 | 3
|  |  |  | Use case diagram | 1 | 1 | 0
|  |  |  | Activity diagram | 1 | 1 | 1 |  | Velocity Chart
|  |  |  | Update the GUI | 2 | 1 | 0
|  |  |  | Write the code | 1 | 2 | 1
|  |  |  | Test | 2 | 0 | 1
10 | Low | Dima | 20 | As an administrator, I want to be able to select the prices of different cars, in order to control prices. | 7 | 4 | 2
|  |  |  | Create Edit Cars Tab in GUI | 1 | 0 | 0
|  |  |  | Implementing add a car button and functions for this button | 2 | 1 | 0
|  |  |  | Implementing edit a car button and functions for this button | 1 | 2 | 0
|  |  |  | SQL statements to get the useful data from the database | 2 | 1 | 1
|  |  |  | Testing | 1 | 0 | 1
14 | Medium | Nicoleta | 10 | As a user, I want to be able to add money to my wallet | 8 | 3 | 1
|  |  |  | Use case diagram | 1 | 0 | 0
|  |  |  | Activity diagram | 1 | 0 | 0
|  |  |  | Update the GUI | 2 | 1 | 0
|  |  |  | Write the code | 2 | 1 | 0
|  |  |  | Test | 2 | 1 | 1
Total |  |  | 45 |  | 22 | 12 | 6
40

## Sprint 5
|  |  |  | Group 2 | Product Backlog
|  |  |  | Rental Car Project | "Europcar"
|  |  |  | Deadline Estimate / Today | 2019-06-07 | 2019-06-07 | Left days: | 0
|  |  |  | How many percent are done | 100
|  |  |  | ? | ? |  | Done
|  |  |  | ? | ? | ? | In Progres
|  |  |  | Number of hours Estimate/Actual | 5 | 54.75 | Not Started
Product Backlog
ID | Priority | Responsible | Estimate | Item | Day 1 | Day 2 | Day 3
7 | Medium | Justinas | 5 | As a user, I want to be able to cancel my reservation in order to not rent a vehicle. | 5 | 2 | 3
|  |  |  | Use case diagram | 0 | 0 | 3
|  |  |  | Activity diagram | 0 | 2 | 0 |  | Velocity Chart
|  |  |  | Update the GUI | 2 | 0 | 0
|  |  |  | Write the code | 2 | 0 | 0
|  |  |  | Test | 1 | 0 | 0
|  |  |  | Project Report | 9.5 | 7 | 10.75
|  |  |  | Intoduction | 1 | 0 | 0.25
|  |  |  | Requirements | 0.5 | 0 | 1.5
|  |  |  | Analysis | 1 | 1 | 3
|  |  |  | Design | 2 | 3 | 3
|  |  |  | Implementation | 1 | 2 | 1
|  |  |  | Test | 3 | 1 | 0.5
|  |  |  | Result and Discusion | 0.5 | 0 | 0
|  |  |  | Conclusion | 0.5 | 0 | 0
|  |  |  | Project Future | 0 | 0 | 0.5
|  |  |  | Source of Information | 0 | 0 | 0.5
|  |  |  | Appendices | 0 | 0 | 0.5
|  |  |  | Process Report | 6.75 | 3.25 | 7.5
|  |  |  | Introduction | 1 | 0.25 | 0.25
|  |  |  | Group Description | 1.5 | 0 | 0.25
|  |  |  | Gorup Initiation | 0.5 | 0 | 1.5
|  |  |  | Group Execution | 2 | 1 | 2
|  |  |  | Personal Reflection | 1 | 1 | 1
|  |  |  | Supervison | 0.5 | 1 | 1.5
|  |  |  | Conclusion | 0.25 | 0 | 1
Total |  |  | 5 |  | 21.25 | 12.25 | 21.25
54.75

## r1
Final
Total Actual | 183.45 | 103 | 46.25 | 0
Total Planned | 185 | 123.3333 | 61.6667 | 0
Total Planned | 185 | 123.3333 | 61.6667 | 1
Sprint 1
Total Actual | 55 | 30 | 20.5 | 19
Total | 55 | 25 | 4.5 | -14.5
Expected | 55 | 36.6667 | 18.3333 | 0
Sprint 2
Total Actual | 60 | 14.45 | 8.25 | 6.25
Total | 60 | 45.55 | 37.3 | 31.05
Expected | 60 | 40 | 20 | 0
Sprint 3
Total Actual | 20 | 9 | 9 | 9
Total | 20 | 13.3333 | 6.6667 | 0
Sprint 4
Total Actual | 45 | 22 | 12 | 6
Total | 45 | 30 | 15 | 0
Sprint 5
Total Actual | 30 | 0 | 19 | 0
Total | 55 | 36.6667 | 18.3333 | 0
Sprint 6
Total Actual | 30 | 0 | 19 | 0
Total | 55 | 36.6667 | 18.3333 | 0
Sprint 7
Total Actual | 30 | 0 | 19 | 0
Total | 55 | 36.6667 | 18.3333 | 0
[5 empty] | Session | Date | Content | Preparation | Resources and activities | Links
[5 empty] | Sprint #1, day 2 | 04 Apr 08:20 – 16:05 | Every group has a Daily SCRUM meeting(documented outcome: updated burndown chart, log/resume if task responsible or ressources changed) See e.g. https://agilevelocity.com/scrummaster/daily-scrum-cheat-sheet/ | Finish your tasks |  | https://agilevelocity.com/scrummaster/daily-scrum-cheat-sheet/
[5 empty] | Sprint #1, day 3 | 11 Apr 08:20 – 16:05 | Every group has a Daily SCRUM meeting (documented outcome: updated burndown chart, log/resume if task responsible or ressources changed) | Finish your tasks
[5 empty] | Sprint #1 ends, Sprint #2 starts | 25 Apr 08:20 – 16:05 | Every group has a Sprint 1 review meeting (documented outcome: list of the approved or rejected product backlog items (completed/not completed) from Product owners after the presentation, updated burndown chart, Log/summary for meeting, Completed and tested code, Diagrams and documentation/work papers) a Sprint 1 retrospective meeting (documented outcome: list of aggreed start-stop-continue areas, Log/summary for meeting) some time to update the Product backlog (outcome: updated product backlog with completed items, newly rearranged items, new items, deleted items - and reestimated items and higher priority items described in more details) a Sprint 2 planning meeting (documented outcome: Sprint 2 goal, Sprint 2 Backlog including responsible person for each task, Log/summary for the meeting and expected UP phase) About review, see e.g. link About retrospective, see e.g. link About planning, see e.g. link | Finish Sprint 1 tasks - after meetings, upload documented outcome to your group folder |  | https://codehollow.com/scrum-meeting-templates/sprint-review-template/ https://agilevelocity.com/scrummaster/retrospective-cheat-sheet/ https://www.leadingagile.com/2012/08/simple-cheat-sheet-to-sprint-planning-meeting/
[5 empty] | Sprint #2, day 2 | 02 May 08:20 – 16:05 | Daily SCRUM meeting
[5 empty] | Sprint #2, day 3 | 09 May 08:20 – 16:05 | Daily SCRUM meeting
[5 empty] | Sprint #2, ends, Sprint #3 starts | 16 May 08:20 – 16:05 | Review meeting Retrospective meeting Update Product backlog Sprint planning meeting
[5 empty] | Sprint #3, day 2 | 20 May 08:20 – 16:05
[5 empty] | Sprint #3, day 3 | 21 May 08:20 – 16:05
[5 empty] | Sprint #3 ends, Sprint #4 starts | 22 May 08:20 – 16:05
[5 empty] | Sprint #4 day 2 | 23 May 08:20 – 16:05
[5 empty] | Sprint #4, day 3 | 24 May 08:20 – 16:05
[5 empty] | Sprint #4, ends, Sprint #5 starts | 27 May 08:20 – 16:05
[5 empty] | Sprint #5, day 2 | 28 May 08:20 – 16:05
[5 empty] | Sprint #5, day 3 | 29 May 08:20 – 16:05
[5 empty] | Sprint #5 ends, Sprint #6 starts | 30 May 08:20 – 16:05
[5 empty] | Sprint #6 day 2 | 31 May 08:20 – 16:05
[5 empty] | Sprint #6, day 3 | 03 Jun 08:20 – 16:05
[5 empty] | Sprint #6 ends, Sprint #7 starts | 04 Jun 08:20 – 16:05
[5 empty] | Sprint #7, day 2 | 05 Jun 08:20 – 16:05
[5 empty] | Sprint #7, day 3 | 06 Jun 08:20 – 16:05
[5 empty] | Final deadline (end of Sprint #7) | 07 Jun 08:20 – 16:05 |  | Hand-in before 12 noon

## r1 (2) (hidden)
2019-06-14
2019-06-15
2019-06-16
2019-06-17
|  | Day 1 | Day 2 | Day 3 | Day 4 | [5 empty] | 2019-06-18
Final
Total Actual |  | 183.45 | 103 | 46.25 | 0 | Day 1 | Day 2 | Day 3 | Day4
Total Planned |  | 185 | 123.3333 | 61.6667 | 0
Total Planned |  | 185 | 123.3333 | 61.6667 | 1 | 185 | 123.3333 | 61.6667 | 0
Sprint 1 | [5 empty] | 0 | 56.75 | 46.25 | 0
| 0 | 30 | 20.5 | 19 | 0
Total
| 73.3333 | 55 | 36.6667 | 18.3333 | 0
Sprint 2 | [5 empty] | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14 | Day 15 | Day 16 | Day 17 | Day 18 | Day 19 | Day 20 | Day 21 | Day 22
Total Actual |  | 60 | 14.45 | 8.25 | 6.25 | 185 | 176.1905 | 167.381 | 158.5714 | 149.7619 | 140.9524 | 132.1429 | 123.3333 | 114.5238 | 105.7143 | 96.9048 | 88.0952 | 79.2857 | 70.4762 | 61.6667 | 52.8571 | 44.0476 | 35.2381 | 26.4286 | 17.619 | 8.8095 | 8.8095
Total |  | 60 | 45.55 | 37.3 | 31.05 | 54 | 3 | 24 | 2 | 23 | 3 | 2 | 1 | 0 | 2 | 23 | 3 | 3 | 3 | 4 |  | 2 | 2 | 4 | 5 | 2 | 3
Expected |  | 60 | 40 | 20 | 0
Sprint 3
Total Actual |  | 20 | 9 | 9 | 9
Total |  | 20 | 13.3333 | 6.6667 | 0
Sprint 4
Total Actual |  | 45 | 22 | 12 | 6
Total |  | 45 | 30 | 15 | 0
Sprint 5
Total Actual |  | 30 | 0 | 19 | 0
Total |  | 55 | 36.6667 | 18.3333 | 0
Sprint 6
Total Actual |  | 30 | 0 | 19 | 0
Total |  | 55 | 36.6667 | 18.3333 | 0
Sprint 7
Total Actual |  | 30 | 0 | 19 | 0
Total |  | 55 | 36.6667 | 18.3333 | 0
[6 empty] | Session | Date | Content | Preparation | Resources and activities | Links
[6 empty] | Sprint #1, day 2 | 04 Apr 08:20 – 16:05 | Every group has a Daily SCRUM meeting(documented outcome: updated burndown chart, log/resume if task responsible or ressources changed) See e.g. https://agilevelocity.com/scrummaster/daily-scrum-cheat-sheet/ | Finish your tasks |  | https://agilevelocity.com/scrummaster/daily-scrum-cheat-sheet/
[6 empty] | Sprint #1, day 3 | 11 Apr 08:20 – 16:05 | Every group has a Daily SCRUM meeting (documented outcome: updated burndown chart, log/resume if task responsible or ressources changed) | Finish your tasks
[6 empty] | Sprint #1 ends, Sprint #2 starts | 25 Apr 08:20 – 16:05 | Every group has a Sprint 1 review meeting (documented outcome: list of the approved or rejected product backlog items (completed/not completed) from Product owners after the presentation, updated burndown chart, Log/summary for meeting, Completed and tested code, Diagrams and documentation/work papers) a Sprint 1 retrospective meeting (documented outcome: list of aggreed start-stop-continue areas, Log/summary for meeting) some time to update the Product backlog (outcome: updated product backlog with completed items, newly rearranged items, new items, deleted items - and reestimated items and higher priority items described in more details) a Sprint 2 planning meeting (documented outcome: Sprint 2 goal, Sprint 2 Backlog including responsible person for each task, Log/summary for the meeting and expected UP phase) About review, see e.g. link About retrospective, see e.g. link About planning, see e.g. link | Finish Sprint 1 tasks - after meetings, upload documented outcome to your group folder |  | https://codehollow.com/scrum-meeting-templates/sprint-review-template/ https://agilevelocity.com/scrummaster/retrospective-cheat-sheet/ https://www.leadingagile.com/2012/08/simple-cheat-sheet-to-sprint-planning-meeting/
[6 empty] | Sprint #2, day 2 | 02 May 08:20 – 16:05 | Daily SCRUM meeting
[6 empty] | Sprint #2, day 3 | 09 May 08:20 – 16:05 | Daily SCRUM meeting
[6 empty] | Sprint #2, ends, Sprint #3 starts | 16 May 08:20 – 16:05 | Review meeting Retrospective meeting Update Product backlog Sprint planning meeting
[6 empty] | Sprint #3, day 2 | 20 May 08:20 – 16:05
[6 empty] | Sprint #3, day 3 | 21 May 08:20 – 16:05
[6 empty] | Sprint #3 ends, Sprint #4 starts | 22 May 08:20 – 16:05
[6 empty] | Sprint #4 day 2 | 23 May 08:20 – 16:05
[6 empty] | Sprint #4, day 3 | 24 May 08:20 – 16:05
[6 empty] | Sprint #4, ends, Sprint #5 starts | 27 May 08:20 – 16:05
[6 empty] | Sprint #5, day 2 | 28 May 08:20 – 16:05
[6 empty] | Sprint #5, day 3 | 29 May 08:20 – 16:05
[6 empty] | Sprint #5 ends, Sprint #6 starts | 30 May 08:20 – 16:05
[6 empty] | Sprint #6 day 2 | 31 May 08:20 – 16:05
[6 empty] | Sprint #6, day 3 | 03 Jun 08:20 – 16:05
[6 empty] | Sprint #6 ends, Sprint #7 starts | 04 Jun 08:20 – 16:05
[6 empty] | Sprint #7, day 2 | 05 Jun 08:20 – 16:05
[6 empty] | Sprint #7, day 3 | 06 Jun 08:20 – 16:05
[6 empty] | Final deadline (end of Sprint #7) | 07 Jun 08:20 – 16:05 |  | Hand-in before 12 noon